## PGO53- Project Management
SET | TYPE | MARKS | QUESTION | CO | PI | Bloom's Level | Accessible For | ANSWER-ONE | ANSWER-ONE-STATUS | ANSWER-TWO | ANSWER-TWO-STATUS | ANSWER-THREE | ANSWER-THREE-STATUS | ANSWER-FOUR | ANSWER-FOUR-STATUS | ANSWER-FIVE | ANSWER-FIVE-STATUS | ANSWER-SIX | ANSWER-SIX-STATUS
A | SINGLE-CORRECT | 1 | Project management includes judgemental sampling in addition to random and systematic sampling. | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | Only True for Statistical projects | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Periodically Project Risk Review team meetings ensure which of the following: | CO1 |  | Remember | My Institute | Time and Cost | Incorrect | Time and Cost but not Scope | Incorrect | Time, Cost, OPEX but not scope | Incorrect | Time, Cost and Scope | Correct
A | SINGLE-CORRECT | 1 | When are risks plotted into a Hits vs Distribution intervals curve? | CO2 |  | Apply | My Institute | Pre-Mitigation | Incorrect | During Mitigation | Incorrect | Post-Mitigation | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following is true about the flow of project management while designing the packaging of an aerated drinks? | CO2 |  | Apply | My Institute | Business objective-> Project challenge-> Design challenge->Development process->Final Solution | Correct | Project challenge-> Design challenge->Development process->Final Solution | Incorrect | Business objective-> Design challenge->Development process->Final Solution | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | People who can make your project fail will | CO1 |  | Remember | My Institute | be the stakeholder of the project | Correct | not be the stakeholder of the project | Incorrect | may or may not be the stakeholder of the project | Incorrect | This is a wrong parameter to judge | Incorrect
A | SINGLE-CORRECT | 1 | Change management in "Project Charter" is all about? | CO1 |  | Remember | My Institute | How decisions will be made? | Incorrect | How changes will be made? | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following is the last outcome of Auditing a project? | CO2 |  | Apply | My Institute | Mitigation | Incorrect | Assurance | Correct | Assessment | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Mitigation plan of a risk depends upon | CO2 |  | Apply | My Institute | Risk Probability | Incorrect | Risk Impact | Incorrect | Risk timeline | Incorrect | All of these | Correct
A | SINGLE-CORRECT | 1 | Stakeholders who are managed closely usually have | CO1 |  | Understand | My Institute | High power but low interest | Incorrect | Low power and low interest | Incorrect | High interest but low power | Incorrect | High power and high interest | Correct
A | SINGLE-CORRECT | 1 | Which of the following Is the part of Project Charter Template? | CO1 |  | Remember | My Institute | Customer not impacted by the project | Incorrect | Needs tapped by banking partners | Incorrect | When is the communication needed? | Correct | Activity Diagrams | Incorrect
A | SINGLE-CORRECT | 1 | New, Open and Closed Status parameters indicate towards which of the following logs? | CO1 |  | Remember | My Institute | Scope change log | Incorrect | Issue tracking log | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Calculating Variance during Lesson learning phase of Project Management depends upon | CO2 |  | Apply | My Institute | Original Plan | Incorrect | Actual Results | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Project Budget includes | CO1 |  | Remember | My Institute | Deliverables and Contingency | Correct | Deliverables but not contingency | Incorrect | Contingency but not deliverables | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following is true about "Microsoft Project"? | CO1 |  | Remember | My Institute | It is a part of MS office suite | Incorrect | It is a type of project management tool | Correct | It is a type of MS 365 tool | Incorrect | All of these | Incorrect
A | SINGLE-CORRECT | 1 | Managing data over separate systems- MS Excel and MS Project is | CO2 |  | Apply | My Institute | appropriate. | Incorrect | not appropriate. | Correct | something which doesn't matter | Incorrect | something which is decided by non-stake members | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following may impact Project bidding submission? | CO2 |  | Apply | My Institute | Critical Path | Incorrect | Resource loaded schedule | Incorrect | Bill of Quantity | Incorrect | All of these | Correct
A | SINGLE-CORRECT | 1 | Which stakeholder signoff and approves a Project Charter Template? | CO1 |  | Remember | My Institute | Sponsor | Correct | Project Manager | Incorrect | CEO | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Project bidding offers a clearer view on the planned _________ flow. | CO2 |  | Apply | My Institute | operational | Incorrect | cash | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Microsoft Project Tool is able to | CO2 |  | Apply | My Institute | monitor in a better way | Incorrect | control upto the bestest level | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | The demanding Beneficiary needs for Project Management require a continuous process for personnel training in using tools and applying best industry’s practices in planning and controlling the project work. | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Project performance dimensions include | CO2 |  | Apply | My Institute | Time | Incorrect | Cost | Incorrect | Scope | Incorrect | All of these | Correct
A | SINGLE-CORRECT | 1 | Which of the following life path show "Quick momentum" while projecting %completion of a project? | CO2 |  | Apply | My Institute | S shape | Incorrect | J shape | Incorrect | Both of these | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Dummy activity consumes | CO1 |  | Remember | My Institute | most of the times zero time and zero cost | Incorrect | always zero time and zero cost | Correct | most of the times zero time but not zero cost | Incorrect | always zero time but not zero cost | Incorrect
A | SINGLE-CORRECT | 1 | In network analysis, Float has how many types? | CO1 |  | Remember | My Institute | One | Incorrect | Two | Incorrect | Three | Incorrect | Four | Correct
A | SINGLE-CORRECT | 1 | Stakeholders are directly involved in _____ and indirectly involved in ______ among project stages. | CO1 |  | Understand | My Institute | Planning, initiating | Incorrect | Planning, nothing | Incorrect | Initiating, planning | Correct | This question paper is so pathetic, No clue! | Incorrect
A | SINGLE-CORRECT | 1 | Gantt is needed while _______ a project | CO2 |  | Apply | My Institute | Monitoring | Incorrect | Planning | Correct | Both of these | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | A+B = C represents | CO2 |  | Apply | My Institute | Merge event | Correct | Burst event | Incorrect | Both of these | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | When more than one applications get deleted from the operating system of a mobile phone, this represents | CO2 |  | Apply | My Institute | Merge event | Incorrect | Burst event | Correct | Both of these | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Activity duration is | CO1 |  | Remember | My Institute | entire time taken to complete a project | Incorrect | entire time taken to complete all the activities | Incorrect | entire time duration needed to complete a given activity | Correct | All of these | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following statements is most appropriately true about CPM? | CO2 |  | Apply | My Institute | CPM is used to coordinate the activities of a project. | Incorrect | CPM is used to schedule the activites of a project. | Incorrect | CPM is used to coordinate and schedule the sequential activities of a project. | Correct | CPM is used to coordinate and schedule the non-sequential activities of a project. | Incorrect
A | SINGLE-CORRECT | 1 | Dummy activity is represented by ? | CO1 |  | Remember | My Institute | _______ | Incorrect | > | Incorrect | Combination of previous two | Incorrect | None of these | Correct
A | SINGLE-CORRECT | 1 | If a second activity can be started after part of a first activity is complete, a dummy activity is inserted. | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Dummy is inserted to connected the dangling activities | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | The longest-duration path through the network is known as critical path. | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Critical Path is the minimum time required to complete the project | CO1 |  | Understand | My Institute | TRUE | Correct | FALSE | Incorrect | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Activities that lie on the critical path can be delayed without delaying the completion time for the whole project | CO1 |  | Understand | My Institute | TRUE | Incorrect | FALSE | Correct | May be | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | When arrows are drawn from right to left, resulting into error in relationship. This is called _____ error. | CO1 |  | Remember | My Institute | Dangling | Incorrect | Looping | Correct | Both of these | Incorrect | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Which of the following is most appropriately true about "Redundancy"? | CO2 |  | Apply | My Institute | Necessary predecessors are used | Incorrect | Redundance should not be eliminated | Incorrect | Both of these | Incorrect | None of these | Correct
A | SINGLE-CORRECT | 1 | Project management is | CO1 |  | Understand | My Institute | related to operations | Incorrect | related to operations and supplychain | Incorrect | related to production, operations and supplychain | Correct | None of these | Incorrect
A | SINGLE-CORRECT | 1 | Project formulation is | CO1 |  | Understand | My Institute | performed after project appraisal | Incorrect | performed along with project appraisal | Incorrect | not related to project appraisal at all | Incorrect | performed prior to project appraisal | Correct